## TODO
IAC to do
No | Description | Area | Notes | Completed
1 | VNET to be added with two subnets: 1. Private endpoints 2. AppService subnet (delegated to 'Microsoft.Web/serverFarms' | Networking
2 | Route table with default routes to be added | Networking
3 | Assume access to platform URLS included in default firewall rules | Networking
4 | Automate assignment of 'Key Vault Secrets User' on the KeyVault for the following system assigned managed identities: 1. Web App Front End 2. Web App API 3. Cosmos DB 4. Data Factory | RBAC | Permission ID: Key Vault Secrets User: 4633458b-17de-408a-b874-0445c86b69e6
5 | Automate assignment of 'Storage Blob Data Contributor' for managed identity: 1. Data Factory | RBAC | Permission ID: Storage Blob Data Contributor: ba92f5b4-2d11-453d-a403-e96b0029c9fe
6 | Automate assignment of 'Cosmos DB Built-in Data Contributor' for managed identity: 1. Data factory 2. Web App Api | RBAC | Permission ID: Cosmos DB Built-in Data Contributor: 00000000-0000-0000-0000-000000000002 This is not a default build in role. (https://learn.microsoft.com/en-us/answers/questions/994687/missing-cosmos-db-built-in-data-reader-and-cosmos) Following az cli command will show the role details: 'az cosmosdb sql role definition list --account-name nceapoc-snd-cosmosdb --resource-group NCE-IAC-POC'
7 | Automate adding all private endpoints to private dns zones. Ensure private dns zones are integrated with the VNET and are resolvable. | Private endpoints and DNS
8 | Automate assignment of 'AcrPull' to managed identities: 1. Web App Front End 2. Web App API | RBAC | Permission ID: AcrPull: 7f951dda-4ed3-4680-a7ca-43fe172d538d
9 | DevOps service principal added to DevOps project with permissions to deploy to dev azure sub 'AZR-NCE-DEV1' : https://dev.azure.com/defragovuk/DEFRA-NCEA/ | DevOps RBAC | Permission ID: CCOE to define
10 | DevOps service principal added to DevOps project with permissions to push to container registry https://dev.azure.com/defragovuk/DEFRA-NCEA/ | DevOps RBAC | Permission ID: AcrPush: 8311e382-0749-4cb8-b61a-304f252e45ec
11 | Web App Front end to be enabled for 'Entra ID' authentication: App registration to: 1. Require authentication 2. Unauthenticated requests to HTTP 403 Forbidden 3. Access to the web app to be allowed in app registration, select users | Web App Auth
12 | Web App API to be enabled for 'Entra ID' authentication: App registration to: 1. Require authentication 2. Unauthorised to HTTP 401 This needs to be integrated with the API Management API. To be defined. | API App Auth
12 | Access to Azure Dev 'AZR-NCE-DEV1' to be able to manage and troubleshoot infra. Contributor? | Azure RBAC
13 | Automate backup schedule for CosmosDB. LRS for lower environments | Backup
14 | Ingress connectivity to Web Front End. How to restrict? Assume IP restriction however team are not using Defra laptops. | Networking
15 | Ingress API connectivity to APIM. How to restrict? Assume IP restriction however team are not using Defra laptops. | Networking

## Sheet1
Pre-requisites
No | Description
Review available templates: https://dev.azure.com/defragovuk/DEFRA-DEVOPS-COMMON/_git/Defra.Infrastructure.Common?path=/templates/Microsoft.Network
| Git hub actions or dev ops pipelines? | Pieplines and current project
| Is it possible to get a service endpoint created in the SANDBOX to create the end to end devops pipeline | Ali to do
| Role assignments - how do we handle? I intend to use the rbac model. Ideally want to set all of these permissions in the pipeline, e.g webapp can get a secret from the keyvautl | App registration and rbac
A virtual network with: - A private endpoint subnet - An app service subnet with: delegation to 'Microsoft.Web\serverFarms' Service endpoint enabled for 'Microsoft.Web'
Need to know resource ID's of virtual networks and subnets
| Will Azure policy enforce logging to centralised log analytics instance? | Resources Will be connected to central LA.
We will require the resource ID of the centralised log analytics instance for each environment
Finalise naming convention
Need to know how private dns will be handled. Is this done outside of the project pipeline
Will need a service connection created in the project devops instance for SND, DEV and TEST
Will need a DEV OPS agent that can access private endpoints for DEV and TEST
| We will need a mechanism to test access to web apps | Front end ingress point
| How do we manage egress connectivity to other azure resources, internet addresses etc | All egress goes via palo alto.
| How do we manage the API Manager configuration? | TBD. CCOE engineer allocated to work through.
| How do we manage Azure Front door? - Lower environments - Private access to exposed services (assume IP restrictions in WAF policies) - How can we view firewall logs? | F5 silverline
| How do we manage the Entra ID app registrations? | TBD. CCOE engineer allocated to work through.
ALI | Devop engineer
Jevgenijs
Next steps | Ali to catch up and start